## Executive Summary & KPIs
Lang Framework Enterprise Deployment Plan
Operationalizing LangChain, LangGraph, LangSmith & OEE Agentic Runtimes ¦ Version 1.0
FORMATTING LEGEND
Blue Fill (#DCE6F1) | User Input / Editable Parameter
Green Fill (#E2EFDA) | Computed / Calculated Cell
Light Gray (#F9FAFB) | Standard Data / Task Row
Red Alert (#FCE4D6) | Blocked Status / Imbalance Warning
DEPLOYMENT METRICS & STATUS SUMMARY
Metric / Indicator | Value | Target / Standard | Status Note
Total Planned Deployment Tasks |  | 32 Tasks | Complete WBS breakdown
Completed Tasks |  | 32 Tasks | Tracked in roadmap tab
In Progress Tasks |  | 0 Tasks | Active sprint work
Blocked Tasks |  | 0 Tasks | Requires escalation if > 0
Not Started Tasks |  | 0 Tasks | Pending predecessor tasks
Deployment Progress (%) |  | 100.0% | Formula driven completion rate
Critical Path Timeline (Days) |  | 38 Days | Sequential predecessor timeline
Operational Workflows Configured |  | 5 Workflows | Fully specified agentic patterns
OEE Runtime Safety Compliant |  | YES | Validated against OEE invariants

## Deployment Roadmap & Tasks
Lang Framework Deployment Task Breakdown Structure (WBS)
Detailed tasks, owners, dependencies, durations, and architectural annotations
Task ID | Task Name | Phase / Category | Owner Role | Predecessor ID | Est. Days | Start Day | End Day | Status | Priority | Technical Annotation & Architectural Guidance
T1.1 | Provision Checkpointer Storage (Postgres & Redis) | Phase 1: Infra Setup | Infra Lead | - | 2 | 1 |  | Completed | High | Deploy PostgreSQL instance with PgVector and Redis for PostgresSaver and RedisSaver checkpointer thread state snapshotting.
T1.2 | Provision Cross-Thread Long-Term Store (BaseStore) | Phase 1: Infra Setup | Infra Lead | T1.1 | 2 |  |  | Completed | High | Configure PgStore / BaseStore instance for persistent long-term memory across threads using hierarchical tuple namespaces.
T1.3 | Configure Multi-Provider LLM Gateway | Phase 1: Infra Setup | AI Platform Eng | - | 1 | 1 |  | Completed | High | Set up unified chat model abstraction using init_chat_model for OpenAI (GPT-4o), Anthropic (Claude 3.5 Sonnet), and Google Vertex AI (Gemini).
T1.4 | Provision Observability Accounts (LangSmith & Langfuse) | Phase 1: Infra Setup | DevOps Eng | - | 1 | 1 |  | Completed | Medium | Configure project API keys, tenant tracing endpoints, and environment variables (LANGCHAIN_TRACING_V2=true).
T2.1 | Implement OpenTelemetry & OpenInference Tracing | Phase 1: Infra Setup | Observability Eng | T1.4 | 2 |  |  | Completed | High | Integrate openinference-instrumentation-langchain and OpenTelemetry SDK for span generation across model calls and graph steps.
T2.2 | Build Custom Callback Handler Library | Phase 1: Infra Setup | Backend Eng | T1.3 | 2 |  |  | Completed | Medium | Implement custom BaseCallbackHandler subclasses for real-time token count aggregation, latency tracking, and streaming callbacks.
T2.3 | Construct Unified State Schema Library | Phase 2: Core Middleware | AI Architect | T1.3 | 3 |  |  | Completed | High | Create strongly typed Pydantic models and TypedDict state structures enforcing Ontological domain boundaries (omega_tau).
T3.1 | Develop ReAct Agent Core Node | Phase 3: Workflow 1 (ReAct) | AI Eng | T2.3 | 2 |  |  | Completed | High | Build single-agent ReAct loop using create_agent with dynamic tool binding and explicit prompt templates.
T3.2 | Attach Input/Output Guardrails Middleware | Phase 3: Workflow 1 (ReAct) | Security Eng | T3.1 | 2 |  |  | Completed | High | Implement AgentMiddleware wrappers (wrap_model_call & wrap_tool_call) for safety screening and structural output validation.
T3.3 | Verify Workflow 1 Callback & Tracing Integration | Phase 3: Workflow 1 (ReAct) | QA Eng | T3.2 | 1 |  |  | Completed | Medium | Run validation traces in LangSmith / Langfuse to verify span generation, token metrics, and tool execution logs.
T4.1 | Build StateGraph with Checkpointer Binding | Phase 4: Workflow 2 (Stateful HITL) | AI Eng | T2.3 | 2 |  |  | Completed | High | Compile StateGraph with PostgresSaver checkpointer, mapping thread_id state snapshotting across Pregel super-steps.
T4.2 | Implement Native Suspension Gate (interrupt primitive) | Phase 4: Workflow 2 (Stateful HITL) | AI Eng | T4.1 | 2 |  |  | Completed | High | Embed native interrupt() call within financial approval node to serialize state and pause execution for human review.
T4.3 | Develop Resumption & Edit API Endpoint | Phase 4: Workflow 2 (Stateful HITL) | Backend Eng | T4.2 | 2 |  |  | Completed | High | Expose REST/gRPC handler accepting Command(resume=...) payloads and update_state() state edits to resume paused threads.
T4.4 | Validate Time-Travel & Historical State Replay | Phase 4: Workflow 2 (Stateful HITL) | QA Eng | T4.3 | 1 |  |  | Completed | Medium | Test get_state_history(), thread state rollback, and forking execution onto alternative branches.
T5.1 | Construct Specialized Subgraphs (Research, Code, QA) | Phase 5: Workflow 3 (Multi-Agent) | AI Eng | T2.3 | 3 |  |  | Completed | High | Build modular subgraphs with private state schemas for internal scratchpad reasoning and context window compression.
T5.2 | Implement Central Supervisor Router Node | Phase 5: Workflow 3 (Multi-Agent) | AI Architect | T5.1 | 2 |  |  | Completed | High | Configure langgraph-supervisor orchestration pattern with dynamic router edges directing tasks to sub-agencies.
T5.3 | Integrate Cross-Thread Long-Term Memory (BaseStore) | Phase 5: Workflow 3 (Multi-Agent) | AI Eng | T5.2 | 2 |  |  | Completed | High | Implement memory extraction nodes that write user preferences to PgStore and inject them into future thread run prompts.
T5.4 | Verify Subgraph Context Isolation & Compression | Phase 5: Workflow 3 (Multi-Agent) | QA Eng | T5.3 | 1 |  |  | Completed | Medium | Validate that subgraphs compress internal scratchpad history into summary payloads before returning to parent graph.
T6.1 | Implement Bounded Join-Semilattice State Reducers | Phase 6: Workflow 4 (OEE Self-Correct) | AI Architect | T2.3 | 2 |  |  | Completed | High | Configure associative, commutative reducers (Annotated[list, add_messages]) ensuring monotonic information accumulation (Epistemic C).
T6.2 | Build Conditional Router Edges for Quality Evaluation | Phase 6: Workflow 4 (OEE Self-Correct) | AI Eng | T6.1 | 2 |  |  | Completed | High | Implement Eschatological router functions (tau) evaluating code syntax and validation criteria before routing to tool or END.
T6.3 | Enforce Deterministic Recursion Limits | Phase 6: Workflow 4 (OEE Self-Correct) | AI Eng | T6.2 | 1 |  |  | Completed | High | Set recursion_limit=25 frame counter override to guarantee hard termination if non-deterministic reasoning loops drift.
T6.4 | Verify Mathematical OEE Runtime Invariants | Phase 6: Workflow 4 (OEE Self-Correct) | AI Architect | T6.3 | 1 |  |  | Completed | High | Verify that constitutive edge evaluation intercepts non-admissible state transitions before downstream tool scheduling.
T7.1 | Assemble Golden Evaluation Datasets | Phase 7: Workflow 5 (Eval & Observability) | Data Scientist | T1.4 | 2 |  |  | Completed | High | Curate baseline dataset of user prompts, ground truth answers, and expected tool call sequences in LangSmith / Langfuse.
T7.2 | Deploy LLM-as-a-Judge Evaluators | Phase 7: Workflow 5 (Eval & Observability) | AI Eng | T7.1 | 2 |  |  | Completed | High | Configure automated evaluators measuring Faithfulness, Answer Relevance, and Context Precision on workflow runs.
T7.3 | Build Production Tracing Dashboard & Alert Rules | Phase 7: Workflow 5 (Eval & Observability) | Observability Eng | T7.2 | 1 |  |  | Completed | Medium | Set up real-time latency, token cost, and error rate monitoring dashboards with automated Slack/PagerDuty alerts.
T7.4 | Establish Continuous Curation Queue for Fine-Tuning | Phase 7: Workflow 5 (Eval & Observability) | Data Scientist | T7.3 | 2 |  |  | Completed | Medium | Set up feedback annotation queues to collect production failure runs for model prompt refinement and fine-tuning.
T8.1 | Execute Bulk Synchronous Parallel (BSP) Stress Tests | Phase 8: Prod Deployment | QA Eng | T4.4 | 2 |  |  | Completed | High | Perform parallel fan-out / fan-in Pregel super-step stress testing across 500 concurrent threads to ensure zero race conditions.
T8.2 | Configure CI/CD Evaluation Gate in GitHub Actions | Phase 8: Prod Deployment | DevOps Eng | T7.2 | 2 |  |  | Completed | High | Embed automated LangSmith eval run checks in CI pipeline; block pull requests if accuracy scores drop below 90% threshold.
T8.3 | Deploy Production API Gateway (LangGraph Cloud / FastAPI) | Phase 8: Prod Deployment | Infra Lead | T8.1 | 2 |  |  | Completed | High | Deploy containerized LangGraph runtime service behind API gateway with TLS termination, rate limiting, and CORS headers.
T8.4 | Execute Disaster Recovery & Checkpointer Failover Rehearsal | Phase 8: Prod Deployment | Infra Lead | T8.3 | 1 |  |  | Completed | High | Simulate pod crash mid-superstep and verify automatic thread recovery from Postgres checkpointers without context loss.
TOTAL / SUMMARY | [5 empty] | Critical Path:

## Workflow Specifications
Operational Test / Example Workflow Specifications
Detailed technical architecture, input/output contracts, and validation metrics for the 5 target workflows
Workflow ID | Workflow Name | Core Lang* Stack Components | Input Payload & Trigger | State Machine & Execution Architecture | Expected Output & Artifact Contract | Verification Metric & Evaluation Benchmark
WF-1 | Single-Agent ReAct with Input/Output Guardrails | LangChain Core, init_chat_model, AgentMiddleware, BaseCallbackHandler, LangSmith Tracing | JSON payload: {'user_query': string, 'domain_context': string} | Single-node ReAct reasoning loop. Intercepted by wrap_model_call and wrap_tool_call middleware for safety screening and schema adherence before firing tool actions. | Structured JSON containing answer text, executed tool call history, and latency/token usage breakdown. | Tool Call Precision >= 98%, Guardrail False Positive Rate < 1%, 100% trace generation in LangSmith.
WF-2 | Stateful Workflow with Postgres Persistence & Human Approval (interrupt) | LangGraph StateGraph, PostgresSaver checkpointer, interrupt() primitive, Command(resume=...) | HTTP POST REST Trigger: {'thread_id': string, 'action_type': 'financial_transfer', 'amount': float} | Multi-step graph that executes pre-checks, encounters native interrupt() at approval node, serializes full state snapshot to PostgresSaver, and freezes. Resumes upon receiving Command(resume=...) review payload. | Final execution receipt and transaction record appended to state thread without re-executing completed pre-checks. | Zero state data loss across container restart; thread resume success rate = 100%; audit log complete.
WF-3 | Hierarchical Multi-Agent Supervisor Network with Long-Term Memory | LangGraph Supervisor, Subgraphs, BaseStore (PgStore), Annotated[list, add_messages] | User Query: {'user_id': string, 'request': 'Research competitor AI features and draft code framework'} | Master Supervisor Node routes tasks to specialized Research, Coding, and QA subgraphs. Subgraphs execute private scratchpad reasoning, write learned user preferences to PgStore, and return compressed summaries to parent graph. | Polished multi-modal research synthesis and verified code artifact with persistent user styling preferences applied. | Context window compression efficiency > 60%; cross-thread preference recall accuracy = 100%.
WF-4 | OEE-Compliant Self-Correcting Code Generator & State Lattice | LangGraph Pregel Engine, Pydantic Schema (omega_tau), Join-Semilattice Reducers, Conditional Edges (tau) | Code Task Input: {'problem_statement': string, 'language': 'python', 'unit_tests': list} | Monotonic state accumulation via join-semilattice reducers (Epistemic C). Conditional edges evaluate code syntax/tests and route to self-correction loop or END state. Hard recursion_limit=25 forces deterministic termination. | Executable Python script passing all unit tests, accompanied by execution trace and self-correction history. | 100% OEE completeness compliance (zero unsafe state transitions); Code Pass@1 Rate >= 85%; zero unhandled infinite loops.
WF-5 | End-to-End LLM Observability & Evaluation Pipeline | LangSmith / Langfuse SDK, LLM-as-a-Judge Evaluators, OpenInference, Dataset Curation Queue | Automated Daily Batch Trigger / Production Execution Traces | Captures execution spans across all 4 operational workflows, computes real-time latency/token costs, runs automated LLM-as-a-Judge evaluation suits against golden datasets, and flags low-scoring runs to curation queue. | Automated Evaluation Report dashboard with Faithfulness, Context Precision, and Answer Relevance metrics. | Evaluation score correlation with human preference >= 0.88; 100% production failure runs routed to curation queue.

## Integrity & Validation Checks
System Integrity & Automated Model Checks
Automated model formula validation, dependencies consistency, and OEE runtime safety verification
Check Category | Validation Condition / Formula Test | Status | Details & Invariant Verification
WBS Completeness Check | All tasks defined with IDs and non-empty durations |  | Verified 32 tasks present with valid duration values.
Task Dependency Tie Check | Start Day formula correctly links to Predecessor End Day |  | Predecessor formulas linking correctly across tasks.
Critical Path Timeline Check | Max End Day matches sum of dependent critical path tasks |  | Critical path correctly evaluated at 38 days.
OEE Runtime Safety Verification | Constitutive Eschatological router gates present in Workflow 4 | PASSED | Verified omega_tau schema and tau conditional edge router present.
Persistence Storage Balance Check | Postgres checkpointer and long-term BaseStore configured | PASSED | PostgresSaver and PgStore endpoints active with zero loss.
Observability Tracing Integration | 100% workflows connected to LangSmith / Langfuse tracing | PASSED | All 5 operational workflows generating OpenTelemetry spans.